## IJCNN Publicity
IJCNN 2015 Killarney - Publicity Actions checklist
|  | Start Date |  | Completion Date
| sel | Target | Actual | Target | Actual
| 1 |  |  |  |  | Current actions :
1
| 1 | 10Apr2014 | 01May2014 |  | 11May2014, ongoing |  | High quality version of flyer - for journal magazines (4 updated versions over course of campaign - Apr, Jun, Aug, Oct). Find out from Marianne Van Wagner. Executive Coordinator. INNS. Society Offices who the contact is and how to work with this.
1
| 1 | [5 empty] | Flyer distribution :
| 1 | 10Apr2014 | 10May2014 | 17Apr2014 | ongoing |  | make a list of target conferences at which INNS-BOG members and others can be designated to provide a stack of flyers
1
| 1 | [5 empty] | Update IJCNN mass email list : Howell's list, used with INNS & IEEE-CIS permission and awareness (President's are informed for each conference). An update is critical as my list is getting old, and I did NOT get update from Cholewo last year
| 1 | 17Apr2014 | 22Apr2014 | 17May2014 | 29Apr2014 |  | IEEE-CIS list for IJCNN authors (Thomascz Cholewo) - request full list of submitting authors
| 1 | 17Apr2014 | 29Apr, 01May2014 | 17May2014 |  |  | INNS membership list
1
| 1 | [5 empty] | IJCNN mass email sendouts : (needs editing and approval from De-shuang Huang and others)
| 1 | 10Apr2014 |  | 19May2014 |  |  | Initial mass email before students and profs start disappearing for summer
1
| 1 | [5 empty] | Journal Adverts (two months lead time to submit for publication!)
| 1 | 14Apr2014 | 12May2014 | 19May2014 |  |  | right now the key thing is to contact journals to find the right contact and requirements, let them know this is coming!
1
1
Later actions :
Update IJCNN mass email list : Howell's list, used with INNS & IEEE-CIS permission and awareness. An update is critical as my list is getting old, and I did NOT get update from Cholewo last year
|  | see above |  |  |  |  | IEEE-CIS list for IJCNN authors (Thomascz Cholewo) - request full list of submitting authors
|  | see above |  |  |  |  | INNS membership list
|  | 02Jun2014 |  | 24Aug2014 |  |  | search for other, available lists - from emails, websites, etc
|  | 24Aug2014 |  | 27Sep2014 |  |  | do any INNS-BOG members have lists that they can share?
IJCNN mass email sendouts :
|  | 21Apr2014 |  |  |  |  | Initial mass email before students and profs start disappearing for summer
|  | 18Aug2014 |  |  |  |  | End of summer before everyone submerged in starting new semester
|  | 22Sep2014 |  |  |  |  | monthly reminder
|  | 20Oct2014 |  |  |  |  | monthly reminder
|  | 24Nov2014 |  |  |  |  | monthly reminder
|  | 08Dec2014 |  |  |  |  | two notices in month of official deadline
|  | 22Dec2014 |  |  |  |  | two notices in month of official deadline - probably with deadline extension announcement
|  | 12Jan2015 |  |  |  |  | Just before extended, final deadline for paper submissions
|  | 10Apr2014 |  | 18Aug2014 |  |  | High quality version of flyer - for journal magazines (4 updated versions over course of campaign - Apr, Jun, Aug, Oct)
Needs key dates : deadlines (examples adapted from WCCI2014 Beijing below)
November 15, 2014 Special session proposals
November 15, 2014 Competition proposals
December 20, 2014 Tutorial proposals deadline
December 20, 2014 Paper submission deadline
March 15, 2015 Paper acceptance notification
April 15, 2015 Final paper submission deadline
IJCNN2015 Publicity Committee - find out from De-shuang who other members might be.
|  | 19May2014 |  | 18Aug2014 |  |  | regional promotion, maybe in languages of target audience?
|  | 19May2014 |  | 18Aug2014 |  |  | social media challenge for publicity - who has ideas here?
|  | 05May2014 |  |  |  |  | IJCNN2015 Organizing Committee - email reminder or them to :
|  | 23Jun2014 |  |  |  |  | print out & bring the flyer to any conferences they are attending
|  | 15Sep2014 |  |  |  |  | make a list of target conferences, and find volunteers to make sure material gets there
IJCNN 2015 website pages - draft content for some of these as related to publicity
|  | 15Sep2014 |  |  |  |  | Newsgroups, frequency - initially once every two months (eg mid April, June, early August), start-of-each-month starting in September, every 2 weeks starting in mid-November:
Connectionists (I can't get this to work! They ignore my postings)
nabble neuroscience
Cogsci
CESUN (no very active!)
Comp.ai.neural-nets (I no longer get this as of last Dec2011 & have to check if it's still active & changed access)
IEEE-CIS - the new social media (Facebook, Linked-in, maybe Twitter if the occasion arises...)
|  | confirmed : |  |  |  |  | Journal Adverts (two months lead time to submit for publication!)
|  | 14Apr2014 |  | Jul2014 issue |  |  | Neural Networks - will include the announcement in each issue until the IJCNN 2015 deadline for submission. (BigData and IJCNN)
|  | 14Apr2014 |  | Jul2014 issue |  |  | Transactions on Neural Networks and Learning Systems - again, will include the announcement in each issue until the IJCNN 2015 deadline for submission. (BigData and IJCNN)
|  | 01Jun2014 |  | Oct2014 |  |  | IEEE-CIS Computational Intelligence - (was Kay Chen Tan) for 2013 they promised a one-page advert in the November issue
|  | 01Jun2014 |  | Oct2014 |  |  | INNS Magazine - (was Soo-Young Lee) -try to get in every issue until Jan2015
|  | 22Sep2014 |  | Oct2014 |  |  | Evolving Systems journal - Plamen Angelov confirmed 22Sep2014 - two issues by Jan2015 (BigData and IJCNN)
Neural Computing & Applications - John MacIntyre confirmed, ?one or two issues? by Jan2015 (BigData and IJCNN)
|  | 22Sep2014 |  | Oct 2014 |  |  | Society/Magazine/Website Event & Conference Calendars - The idea to ensure that IJCNN2015 is widely posted. (INNS - NN & newsletter, IEEE-TNNLS & Computational Intelligence magazine), and others
Flyer distribution :
make a list of target conferences at which INNS-BOG members and others can be designated to provide a stack of flyers
find INNS-BOG volunteers to make sure material gets there. At same time, get suggestions for other target conferences
INNS member email - ?name? emailed INNS members. Should do again periodically in fall...
Will we be doing ? : (requires $ and special preparations)
My understanding is that budgets argue against :
Conference booths - we decided against WCCI Brisbane, although supposedly our flyer was in the conference bag of attendees
Purchase ad space in journals or magazines
It's worth listing these just in case we want to reconsider for future events.
Website :
| 1 |  |  |  |  | Completed Items
1
| 1 | 10Apr2014 |  | 30Apr2014 Deshuang |  |  | WCCI program packages as distributed in Beijing - IJCNN2015 flyer printed as part of the actual Technical Program that lists all of the papers - which they are probably finalising tomorrow or soon thereafter.
1
x | x | x |  | x |  | x | End of list | x

## Sheet2
flyer16.zip from Yoonsuck Choe |  | width |  |  | height
|  | pixels | cm | dpi | pixels | cm | dpi | kbytes | area (cm^2) | kbytes/area
Ireland photo | cc-aerial-full-rt3-crop.jpg | 5542 | 20 | 703.834 | 1629 | 5 | 827.532 | 2100 | 100 | 21
INNS logo | inns-vector3.pdf |  | 4 |  |  | 1.8 |  | 29.1 | 7.2 | 4.0417
IEE-CIS logo | ieeecis-vector.pdf |  | 4 |  |  | 1.8 |  | 7.4 | 7.2 | 1.0278
“IJCNN” lace-letter | ijcnnk.pdf |  | 6.5 |  |  | 1.5 |  | 5.04 | 9.75 | 0.51692
vector images should be OK for resolution?
“IJCNN” lace-letter may be an issue?